## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
1 | Backend Team | 2026-02-07 | VXML parser returning incorrect next state 'agent' when user selects option 5; middleware not handling agent state | Sprint 1 | Backend Team | Logical | Added explicit agent-state handler in middleware; resets to menu after response | 2026-02-08 | Closed | State machine diagram updated in docs
2 | Backend Team | 2026-02-12 | Keyword mapper routing 'train availability' query to ticket booking flow instead of availability flow | Sprint 2 | Backend Team | Logical | Reordered conditional checks in detect_voice_option(); availability checked before booking | 2026-02-13 | Closed | All keyword routing unit tests now passing
3 | Frontend Team | 2026-02-18 | Bot hearing its own TTS voice output and sending it back as user input causing infinite response loop | Sprint 3 | Frontend Team | Logic / UX | Added isSpeaking flag; stopVoice() called before TTS; mic restarts only in speak() onend callback | 2026-02-19 | Closed | Voice loop fully resolved; tested over 20 cycles
4 | Backend Team | 2026-02-24 | Booking flow state machine resetting to menu after first input (source station) instead of advancing to destination | Sprint 4 | Backend Team | Logical | Fixed state transition in middleware; 'source' state now correctly updates to 'destination' | 2026-02-25 | Closed | All booking flow steps verified end-to-end

## Defect Types
Type Of Defect
Logical
User Interface
Performance
Compatibility
Configuration
Maintainability
Standards
Others