## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US001 | As a developer, I want to build a FastAPI backend that processes IVR session state so users can interact via HTTP endpoints. | Must Have | None | Backend Team | Completed
Sprint 1 | Sprint 1 | US002 | As a developer, I want a VXML decision tree parsed by middleware so IVR flows (booking, PNR, cancel, availability) are correctly routed. | Must Have | US001 | Backend Team | Completed
Sprint 2 | Sprint 2 | US003 | As a user, I want my voice input converted to text and mapped to IVR menu options using keyword detection. | Must Have | US001 | Backend Team | Completed
Sprint 2 | Sprint 2 | US004 | As a user, I want the system to detect intent from natural language using a zero-shot NLP classifier (BART-large-MNLI). | Should Have | US003 | AI Team | Completed
Sprint 3 | Sprint 3 | US005 | As a user, I want an interactive web UI with voice recognition, TTS response, and menu buttons replicating a real IVR phone system. | Must Have | US001,US003 | Frontend Team | Completed
Sprint 3 | Sprint 3 | US006 | As a user, I want the microphone to mute automatically while the system speaks to prevent the bot hearing its own TTS output. | Must Have | US005 | Frontend Team | Completed
Sprint 4 | Sprint 4 | US007 | As a user, I want the IVR to guide me through a multi-step ticket booking flow: source station → destination → travel date → confirm. | Must Have | US002 | Backend Team | Completed

## Sprint Backlog
b
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate (Hrs) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18
US001 | T1 | Set up FastAPI project with folder structure, install dependencies (FastAPI, uvicorn, transformers) | 2026-02-03 | 2026-02-04 | Backend | Setup | Done | 4 | bar: Day 1 to Day 2
US001 | T2 | Create /ivr POST endpoint, /reset endpoint, and in-memory session dict | 2026-02-05 | 2026-02-06 | Backend | API Dev | Done | 2 | bar: Day 1 to Day 13
US002 | T3 | Implement vxml_parser.py: get_main_menu(), booking_flow(), pnr_flow(), cancel_flow(), availability_flow() | 2026-02-07 | 2026-02-09 | Backend | VXML Dev | Done | 2 | bar: Day 3 to Day 4
US002 | T4 | Wire middleware.py to route session states via VXML decision tree | 2026-02-09 | 2026-02-10 | Backend | Integration | Done | 2 | bar: Day 1 to Day 13
US003 | T5 | Build detect_voice_option() keyword mapper for PNR/book/cancel/availability/agent | 2026-02-11 | 2026-02-12 | Backend | NLP Dev | Done | 2 | bar: Day 1 to Day 13
US003 | T6 | Write unit tests for all keyword → menu option mappings | 2026-02-12 | 2026-02-13 | Backend | Testing | Done | 2 | bar: Day 6 to Day 7
US004 | T7 | Integrate facebook/bart-large-mnli zero-shot classifier in intent_model.py | 2026-02-13 | 2026-02-15 | AI Team | AI Integration | Done | 2 | bar: Day 1 to Day 13
US005 | T9 | Build index.html with IVR card, header badge, menu grid buttons, input row | 2026-02-16 | 2026-02-18 | Frontend | UI Dev | Done | 2 | bar: Day 10 to Day 11
US005 | T10 | Implement SpeechRecognition API: onresult live transcript, onend auto-send | 2026-02-18 | 2026-02-19 | Frontend | Voice Dev | Done | 6 | bar: Day 1 to Day 13
US005 | T11 | Implement Text-to-Speech using SpeechSynthesisUtterance for IVR responses | 2026-02-20 | 2026-02-21 | Frontend | Voice Dev | Done | 3 | bar: Day 12 to Day 13
US006 | T12 | Add isSpeaking / isListening flags and stopVoice() to mute mic during TTS | 2026-02-21 | 2026-02-22 | Frontend | Bug Fix | Done | 2 | bar: Day 1 to Day 13
US007 | T13 | Implement multi-step booking flow: source → destination → date → complete in middleware | 2026-02-24 | 2026-02-25 | Backend | Feature | Done | 2 | bar: Day 1 to Day 13
US007 | T14 | Add PNR input, cancel PNR, and train availability flows with correct state transitions | 2026-02-25 | 2026-02-26 | Backend | Feature | ongoing | 2 | bar: Day 13 to Day 14
US008 | T15 | Add /reset endpoint to delete session and return to clean state | 2026-02-27 | 2026-02-28 | Backend | API Dev | Done | 2 | bar: Day 1 to Day 14
US008 | T16 | Full end-to-end test: all 5 IVR flows via voice, text, and menu buttons | 2026-03-01 | 2026-03-02 | Both Teams | Testing | Done | 4 | bar: Day 14
US009 | T17 | Added landing page with "Get Started" button before IVR interface | 28/03/2026 | 29/03/2026 | Frontend | UI Dev | Done | 2 | bar: Day 1 to Day 16
US009 | T18 | Fixed start button not working (DOM issue) | 29/03/2026 | 29/03/2026 | Frontend | Bug Fix | Done | 2 | bar: Day 16
US010 | T19 | Auto IVR start using API call | 29/03/2026 | 30/03/2026 | Frontend | Integration | Done | 2 | bar: Day 1 to Day 18
US010 | T20 | Fixed welcome voice not speaking | 30/03/2026 | 30/03/2026 | Frontend | Voice Fix | Done | 2 | bar: Day 17
US011 | T21 | Enabled continuous voice listening | 30/03/2026 | 30/03/2026 | Frontend | Voice Dev | Done | 3 | bar: Day 1 to Day 18
US011 | T22 | Fixed cancel ticket voice detection | 30/03/2026 | 30/03/2026 | Backend | Bug Fix | Done | 2 | bar: Day 2 to Day 17

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | FastAPI session dict not persisting between requests | Used shared sessions dictionary to maintain state across requests
Sprint 1 | Day 3 | VXML parser returning wrong next state for option 5 | Fixed middleware logic and added reset to menu after customer care option
Sprint 2 | Day 1 | BART model taking too long to load initially | Loaded model at module level to reduce startup delay
Sprint 2 | Day 3 | Voice command 'train availability' going to booking flow | Reordered keyword conditions to prioritize availability detection
Sprint 3 | Day 1 | Speech recognition not working in some browsers | Restricted support to Chrome and added browser warning in UI
Sprint 3 | Day 2 | System capturing its own TTS as input | Added isSpeaking flag and disabled mic during speech output
Sprint 3 | Day 3 | Duplicate API calls due to continuous voice loop | Added isListening check to prevent multiple voice triggers
Sprint 4 | Day 1 | Booking flow resetting after entering source station | Fixed state transition in middleware (source → destination)
Sprint 4 | Day 2 | Start button not working properly | Fixed DOM loading issue and event binding for button click
Sprint 4 | Day 2 | Welcome message not speaking automatically | Handled browser audio restriction using user interaction trigger
Sprint 4 | Day 3 | Cancel ticket voice command not working | Fixed intent detection logic and reordered conditions
Sprint 4 | Day 3 | IVR not starting automatically after UI load | Added API call to /ivr when IVR starts
Sprint 4 | Day 4 | Need landing page before IVR interface | Created start screen with "Get Started" button
Sprint 4 | Day 4 | System not listening continuously after response | Implemented auto-restart of voice recognition after each response

## Retrospection
SL # | Sprint # | Sprint Start Date | Sprint End Date | Team Member | Start Doing | Stop Doing | Continue Doing | Action Taken
1 | 1 | 2026-03-02 | 2026-10-02 | Backend Team | Write API contracts before coding each endpoint | Starting integration without proper testing | Peer review backend middleware logic regularly | Created shared API contract structure and improved session handling
2 | 2 | 2026-11-02 | 15/02/2026 | Backend + AI Team | Load ML models efficiently at startup | Loading model inside request causing delay | Daily checks on model performance and intent accuracy | Moved model initialization to module level and reduced response time
3 | 3 | 16/02/2026 | 23/02/2026 | Frontend Team | Test browser compatibility early | Assuming all browsers support SpeechRecognition | Testing UI and voice features across browsers | Added Chrome-only support notice and improved UI responsiveness
4 | 4 | 24/02/2026 | 2026-02-03 | Both Teams | Document IVR flow and state transitions before coding | Merging features without proper state validation | Daily standup and flow validation across modules | Fixed middleware state transitions and ensured correct IVR navigation
5 | 4 | 28/03/2026 | 30/03/2026 | Both Teams | Design proper user flow before UI implementation | Directly integrating voice without handling browser restrictions | Improve voice UX and continuous listening behavior | Added start screen, fixed voice trigger issues, enabled continuous listening, and improved overall IVR experience